## Table 1
RESPONSIBILITY ALLOCATION MATRIX [Project-Specific Sample; Not Suitable for all Projects]
| Criteria Design |  |  | Detailed Design |  |  | Implementation Documents |  |  | Agency Review |  |  | Construction |  |  | Closeout
| Primary | Secondary | Review | Primary | Secondary | Review | Primary | Secondary | Review | Primary | Secondary | Review | Primary | Secondary | Review | Primary | Secondary | Review
CATEGORY ELEMENT | [18 empty] | LEGEND
A SUBSTRUCTURE
Foundations | [18 empty] | Owner ‐ Owner
Standard Foundations | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | Arch | StEng | GC | GC | ‐ | StEng | GC | ‐ | StEng | O/R ‐ Owner Representative
Special Foundations (LinAcc, MRI, CT) | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | Arch | StEng | GC | GC | ‐ | StEng | GC | ‐ | StEng | Arch ‐ Architect
Slab on Grade | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | StEng | GeoE | Arch,GC | Arch | StEng | GC | GC | ‐ | StEng | GC | ‐ | StEng | GC ‐ Constructor
Excavation & Fill | CivEng | GeoE | Arch,GC | CivEng | GeoE | Arch,GC | CivEng | GeoE | Arch,GC | Arch | CivEng | GC | C | GC | GeoE,CivEng | C | GC | CivEng | StEng ‐ Structural Engineer
Basement Construction | [18 empty] | McE ‐ Mechanical Engineer
Shoring (Design/Build) | CivEng | GeoE, StEng | GeoE,StEng | DBSC | GeoE,StEng | Arch,GC | DBSC | GeoE,StEng | Arch,GC | Arch,GC | DBSC | StEng | DBSC | GC | GeoE,StEng | DBSC | GC | StEng | EE ‐ Electrical Engineer
Walls & Columns | StEng | ‐ | GC | StEng | ‐ | Arch,GC | StEng | ‐ | GC | Arch | StEng | GC | GC | ‐ | StEng | GC | ‐ | StEng | McE ‐ Plumbing Engineer
Waterproofing (Below Grade, Podium) | WtrP | Arch | GC | WtrP | Arch | GC | WtrP | Arch | GC | Arch | WtrP | GC | SC | GC | WtrP | SC | GC | WtrP | V ‐ Vendor / Supplier
LC ‐ Lighting Consultant
B SHELL | [18 empty] | LndArc ‐ Landscape Architect
CivEng ‐ Civil Engineer
Superstructure Primary Structural Steel | StEng | Arch | SC, GC | StEng | Arch | SC, GC | SC | StEng | Arch,GC | Arch | StEng | GC,SC | SC | GC | StEng | SC | GC | StEng | KC ‐ Kitchen Consultant
Floor Construction | StEng |  | GC | StEng |  | Arch,GC | StEng |  | Arch,GC | Arch | StEng | GC | GC,SC |  | StEng | GC,SC |  | StEng | AC ‐ Acoustical Engineer
Roof Construction | StEng | Arch,WtrP | GC | StEng | Arch,WtrP | GC | StEng,WtrP | Arch | GC | Arch | StEng,WtrP | GC | SC | GC | WtrP,Arch | SC | GC | WtrP,Arch | WtrP ‐ Waterproofing Consultant
Exterior Enclosure | [18 empty] | U ‐ Utility Company
Exterior Walls | Arch | StEng,WtrP | DA1 | Arch,WtrP | StEng,DA1 | GC | Arch,WtrP | StEng,DA1 | GC | Arch | DA1 | GC | DA1 | GC | Arch,WtrP | DA1 | GC | Arch | T ‐ IPD Team
Glazing Systems | Arch | Arch,WtrP | DA1 | Arch,WtrP | StEng,DA1 | GC | Arch,WtrP | StEng,DA1 | GC | Arch | DA1 | GC | DA1 | GC | Arch,WtrP | DA1 | GC | Arch | GeoE ‐ Geotechnical Engineer
Panelized Systems | Arch | Arch,WtrP | DA1 | Arch,WtrP | StEng,DA1 | GC | Arch,WtrP | StEng,DA1 | GC | Arch | DA1 | GC | DA1 | GC | Arch,WtrP | DA1 | GC | Arch | AG ‐ Agency (Local)
LvEng ‐ Low Voltage Engineer
C INTERIORS | [18 empty] | FSD ‐ Food Service Designer
Interior Construction | [18 empty] | FSC ‐ Food Service Contractor
Partitions | Arch |  | GC | Arch |  | GC | Arch | GC | Team | Arch |  | GC | GC | Arch | Team | GC |  | Arch | ElecTr ‐ Electrical Design‐Assist Trade
Doors | Arch | Owner | GC | Arch |  | GC,EE | GC | Arch | Team | Arch |  | GC | GC | Arch | Team | GC |  | Arch | MecTr ‐ Mechanical Design‐Assist Trade
Stairs | [18 empty] | PlbT ‐ Plumbing Design‐Assist Trade
Stair Construction | Arch | StEng | GC | Arch | StEng | GC | DBSC | GC | Arch | DBSC | Arch | GC | DBSC | GC | StEng,Arch | DBSC | GC | Arch | FPDB ‐ Fire Protection Design‐Builder
Stair Finishes | Arch | Owner | Team | Arch |  | Team | Arch | GC | Team | Arch |  | GC | DBSC | GC | Arch | DBSC | GC | Arch | C1 ‐ Fire Protection Design/Builder
Interior Finishes | [18 empty] | DA1 ‐ Skin Design‐Assist Contractor
Wall Finishes | Arch | Owner | Team | Arch |  | Team | Arch | SC | GC | Arch |  | GC | SC | GC | Arch | SC | GC | Arch | OV ‐ Owner Vendor
Floor Finishes | Arch | Owner | Team | Arch |  | Team | Arch | SC | GC | Arch |  | GC | SC | GC | Arch | SC | GC | Arch | SC ‐ Subcontractor installing the particular element
Ceiling Finishes | Arch | Owner | Team | Arch |  | Team | Arch | SC | GC | Arch |  | GC | SC | GC | Arch | SC | GC | Arch | DBSC ‐ Design‐Build Subcontractor responsible for that element
D SERVICES
Conveying
Elevators & Lifts | Arch | Owner | Team | Arch | StEng | Team | SC | GC | Team | Arch | SC | GC | SC | GC | Arch | SC | GC | Arch
Plumbing
Plumbing Fixtures (Domestic Water) | McE,Arch | PlbT | Team | McE | PlbT | Team | PlbT | McE | Team | Arch | PlbT,McE | GC | PlbT | GC | McE,Arch | PlbT | GC | McE,Arch
Domestic Water Distribution | McE,Arch | PlbT | Team | McE | PlbT | Team | PlbT | McE | Team | Arch | PlbT,McE | GC | PlbT | GC | McE,Arch | PlbT | GC | McE,Arch
Sanitary Waste | McE,Arch | PlbT | Team | McE | PlbT | Team | PlbT | McE | Team | Arch | PlbT,McE | GC | PlbT | GC | McE,Arch | PlbT | GC | McE,Arch
Rain Water Drainage | McE,Arch | PlbT | Team | McE | PlbT | Team | PlbT | McE | Team | Arch | PlbT,McE | GC | PlbT | GC | McE,Arch | PlbT | GC | McE,Arch
HVAC
Energy Supply | McE,Arch | MecTr,ElecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Heat Generating Systems | McE,Arch | MecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Cooling Generating Systems | McE,Arch | MecTr,ElecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Distribution Systems | McE,Arch | MecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Terminal & Package Units | McE,Arch | MecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Controls & Instrumentation | McE,Arch | MecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
System Testing & Balancing | McE,Arch | MecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Other HVAC Systems & Equipment | McE,Arch | MecTr,ElecTr | Team | McE | MecTr | Team | MecTr | McE | Team | Arch | MecTr,McE | GC | MecTr | GC | McE,Arch | MecTr | GC | McE,Arch
Fire Protection
Sprinklers | Arch | FPDB | Team | FPDB | Arch | Team | FPDB |  | Arch,GC | FPDP | Arch | GC | FPDB | GC | Arch | FPDB | GC | Arch
Standpipes | Arch | FPDB | Team | FPDB | Arch | Team | FPDB |  | Arch,GC | FPDP | Arch | GC | FPDB | GC | Arch | FPDB | GC | Arch
Fire Protection Specialties | Arch | FPDB | Team | FPDB | Arch | Team | FPDB |  | Arch,GC | FPDP | Arch | GC | FPDB | GC | Arch | FPDB | GC | Arch
Ansul System (Café) | Arch | FPDB | Team | FPDB | Arch | Team | FPDB |  | Arch,GC | FPDP | Arch | GC | FPDB | GC | Arch | FPDB | GC | Arch
Pre‐Action Systems | Arch | FPDB | Team | FPDB | Arch | Team | FPDB |  | Arch,GC | FPDP | Arch | GC | FPDB | GC | Arch | FPDB | GC | Arch
Electrical
Electrical Service | EE | ElecTr | Team | EE | ElecTr | Team | ElecTr | EE | Team | Arch | ElecTr, EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Lighting and Branch Wiring | EE | ElecTr | Team | EE | ElecTr | Team | ElecTr | EE | Team | Arch | ElecTr, EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Lighting and Branch Wiring | EE | ElecTr | Team | EE | ElecTr | Team | ElecTr | EE | Team | Arch | ElecTr, EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Communications and Security | EE | ElecTr | Team | EE | ElecTr | Team | ElecTr | EE | Team | Arch | ElecTr, EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Fire Alarm | EE | ElecTr | Team | EE | ElecTr | Team | ElecTr | EE | Team | ElecTr | Arch EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
IT & Telecom | EECOM | ElecTr | Team | EECOM | ElecTr | Team | ElecTr | EECOM | Team | Arch | ElecTr,LvEng | GC | ElecTr | GC | LvEng,Arch | ElecTr | GC | LvEng,Arch
E EQUIPMENT & FURNISHINGS
Equipment
Kitchen Equipment | Owner | Arch | Team | FSD | Team | Team | FSD | FSC | Team | FSC | FSD | Team | FSC | GC | Arch | FSC | GC | FSD,Arch
Medical Equipment | Owner | Arch | Team | Vendor | Team | Team | Vendor | Arch | Team | Arch | Vendor | GC | Vendor | GC | Arch | Vendor | Owner | GC,Arch
Medical Equipment Procurement | Owner | O/R | Team | Owner | O/R | Team | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐ | ‐
Above‐Ceiling Bracing & Supports | Arch | StEng | Team | StEng | Arch | Team | StEng | Arch | GC | Arch | StEng | GC | GC | SC | Arch,StEng | GC | SC | Arch
Furnishings
Fixed Furnishings (Custom/Med Casework) | Owner | Arch | Team | Arch | SC | Team | SC | Arch | GC,PlbT | Arch | SC | GC | SC | GC | Arch | SC | GC | Arch
Moveable Furnishings & Systems Furniture | Owner | Arch | GC | Arch | OV | Team | OV | Arch | GC | Arch | OV | GC | OV | GC | Arch | OV |  | GC/Arch
F SPECIAL CONSTRUCTION & DEMOLITION
Special Construction
Selective Building Demolition
Demolition | Arch |  | GC | Arch |  | GC | Arch |  | GC | Arch | GC | ‐ | SC | GC | Arch | GC | SC | Arch
Hazardous Waste Remediation | OV | O/R | GC,Arch | OV |  | GC,O/R | OV | GC | O/R,Arch | Arch,GC |  |  | OV | GC | O/R,Arch | OV |  | Team
G BUILDING MecTrTEWORK
Site Preparation
Site Clearing | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Site Demolition & Relocation | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Site Earthwork | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Hazardous Waste Remediation | GeoE | Owner | Team
Off‐Site Improvements
Sidewalks | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
Bulbouts | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
Roadways | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
Striping & Signage | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
Construction Traffic Management Plan | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
Utility Tie‐Ins | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | SC | GC | CivEng,Arch | GC | NA | CivEng,Arch
Easements | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | CivEng | Arch | GC | GC | NA | CivEng,Arch | GC | NA | CivEng,Arch
On‐Site Improvements
Roadways | CivEng | Arch | Owner,GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Parking Lots | CivEng | Arch | Owner,GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Pedestrian Paving | CivEng | Arch | Owner,GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Site Development | CivEng | Arch | Owner,GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Landscaping | Arch | LndArc,CivEng | Owner,GC | LndArc,CivEng | Arch | GC | SC | LndArc,CivEng | GC,Arch | Arch | LndArc,CivEng | GC | SC | GC | LndArc,Arch | SC | GC | LndArc,Arch
Site Civil/Mech. Utilities
Water Supply & Distribution Systems | CivEng | Arch | GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Sanitary Sewer Systems | CivEng | Arch | GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Stormwater Systems | CivEng | Arch | GC | CivEng | Arch | GC | SC | CivEng | GC,Arch | Arch | CivEng | GC | SC | GC | CivEng,Arch | SC | GC | CivEng,Arch
Site Electrical Utilities
Electrical Distribution | EE,CivEng | ElecTr,Arch | GC | CivEng | EE,ElecTr | Arch,GC | ElecTr | EE | GC,Arch | Arch | ElecTr,EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Site Lighting | EE,CivEng | ElecTr,Arch | GC | EE | ElecTr,CivEng | Arch,GC | ElecTr | EE | GC,Arch | Arch | ElecTr,EE | GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Site Communications & Safety | Arch | Owner | ElecTr,LvEng | LvEng | ElecTr,CivEng | Arch,GC | ElecTr | LvEng | GC,Arch | Arch | ElecTr,LvEng | GC | ElecTr | GC | LvEng,Arch | ElecTr | GC | LvEng,Arch
PG&E Coordination | ElecTr | EE | Arch,GC | EE | ElecTr | Arch,GC | ElecTr | EE | GC,Arch | ElecTr | EE | Arch,GC | ElecTr | GC | EE,Arch | ElecTr | GC | EE,Arch
Note on T7: Author: Teams may want to identify the name of the company next to each role below.